CIVIC LAB / THREE MINUTE BRIEF

6 WEEKS

a bounded pilot with a clear review point

# Library After Hours Pilot

Test one late opening each week before committing to a permanent change.

This fictional presentation handout proposes Thursday openings until 21:00. Attendance, staffing and quiet-study demand will determine the next decision.

# The Need

Evening visitors need access after work and classes. The pilot tests demand rather than assuming every weekday should open later.

| Measure | Collection | Review |
| --- | --- | --- |
| Visitors | Hourly count | Demand by hour |
| Quiet seats | Occupied / available | Capacity pressure |
| Staff hours | Scheduled and actual | Operating effort |

# The Experiment

Open on six Thursdays. Keep a quiet study zone, a staffed help point and a clear closing routine. Record occupancy every hour.

# The Decision

Continue only if demand is sustained and the staffing plan is workable. Publish the measured results, including low-attendance evenings.

Pilot proposal only · Synthetic example, not a funded program.